## Slide 1
Medicaid Updates
October 23, 2019

## Slide 2: Agenda
Managed Care Open Enrollment
EB Outreach Specialist Onsite Support
Provider Enrollment Deadline
Carolina Complete Health Now Serving Region 3, 4 and 5
Expanded/Former Foster Care Children

## Slide 3: Medicaid Transformation Updated Timeline
Jan.
Feb.
Sept.
Oct.
Dec.
July
Aug.
7/15/2019 – 12/13/2019
Open Enrollment
Beneficiaries Select
Health Plan
10/14/2019 -12/13/2019
Open Enrollment
Beneficiaries Select
Health Plan
02/01/2020
Managed Care Day 1
Health Plan Effective Date
Nov.
PHASE 1: Regions 2 & 4
PHASE 2: Regions 1, 3, 5 & 6
June
2019
2020
7/8/2019
Enrollment
Packets Begin
10/01/2019
Enrollment
Packets Begin
Auto-Assignment
Reminder Postcard
NEMT:
Beneficiaries can begin contacting Health Plans on January 1, 2020 for trips scheduled on or after February 1, 2020

## Slide 4: Open Enrollment – Managed Care
Phase 2 Open Enrollment began Monday, October 14
  Enrollment packets were mailed beginning September 30
  All enrollment packets were mailed for beneficiaries in Regions 1, 3, 5, and 6 with eligibility through February 2020 or later.
  As recertifcations are completed, those Mandatory or Exempt beneficiaries with eligibility ending prior to February 1, 2020 will receive notices
  All contact information may be found in the County Playbook under the Enrollment tab at https://medicaid.ncdhhs.gov/counties/county-playbook-medicaid-managed-care/county-playbook-enrollment-materials
Open Enrollment for ALL counties will end December 13
Notes: Phase 2 open enrollment began 10/14 and will run through 12/13; as a reminder, Phase 1 open enrollment continues through 12/13/19 as well. Outreach materials were shipped week of October 7th to phase 2 counties. Phase 1 counties will have outreach materials replenished through their assigned Outreach Specialist. Notify them if you need any material replenished.

## Slide 5: EB Outreach Specialist Onsite Support
Phase 2 Enrollment Broker Outreach onsite support are being rolled out in three waves:
  October 14
  October 21
  October 28 – All counties expected to have support
Directors are contacted the week prior by EB DSS Liaison to work out details, reporting location, etc.
Please review listserv message sent 10/9:
  Total number of outreach specialists designated for each county
  Required arrangements needed for Outreach Specialist
Reminders
Outreach Specialists in the DSS are for beneficiaries who physically come to the DSS for enrollment assistance.
Transfer/refer all appropriate phone calls to Enrollment Broker Call Center at 833-870-5500
Notes: Include plan basics, refer to communication sent to counties re: support, reminders about needs of OS, and purpose of the onsite support to assist those who appear at the agency – not phone calls that come into the agency.
In order for the sufficient number of outreach specialists to be hired and trained, Phase 2 Enrollment Broker Outreach onsite support will be rolled out in three waves beginning on October 14, 2019.
October 14, 2019
October 21, 2019
October 28, 2019
Outreach specialist assignments will be shared with counties prior to being on on-site. In preparation, please make arrangements based on the listserv message sent on 10/9 with the total number of outreach specialists designated to your county and number of days of the week that they will be on-site when fully implemented on October 28, 2019. Counties who will have an enrollment broker outreach specialist on-site starting the week of October 21, 2019, will be notified the week of October 14, 2019. Counties who will have an enrollment broker outreach specialist on-site starting the week of October 28, 2019, will be notified the week of October 21, 2019.
As a reminder, the onsite Outreach Specialist is present for those beneficiaries who come to the DSS office seeking assistance with choice counseling and enrollment. Calls coming into the DSS requesting assistance with enrollment should not be transferred to the onsite Outreach Specialist but transferred or referred to the Enrollment Broker Call Center toll-free at 1-833-870-5500.

## Slide 6: Provider Enrollment Deadline for Auto-assignment
Providers have deadline of November 15 to submit signed contracts to Health Plans in order to be included in the auto-assignment process beginning December 16th
  Providers notified via Special Bulletin
  Refer providers to the Provider Tab on the NC Medicaid website
    Provider Playbook for Managed Care contains training courses, readiness materials, and other helpful resources
Notes: Refer to communications sent; November 15th deadline to be included in auto-assignment process; include where to refer any providers who reach out to the DSS regarding enrollment, etc.
Providers have a deadline of November 15 to submit signed contracts to Health Plans in order to be included in the auto-assignment process during the week of December 16.
A Special Bulletin was issued this week alerting providers that contracts must be signed and submitted to health plans by November 15 to ensure inclusion in auto-assignment process occurring in December. Additionally, counties have reported that providers contact them inquiring about what they need to do or to whom they should speak about Managed Care.
Please refer providers with questions to the Provider tab on the NC Medicaid website. The Provider Playbook for Managed Care contains beneficiary materials, readiness materials, training courses, and other helpful resources.

## Slide 7: Carolina Complete Health – Now covering Region 3, 4, and 5
On October 8, 2019, DHHS announced that in addition to counties in regions 3 and 5, Medicaid beneficiaries Region 4 counties will have the option to choose Carolina Complete Health, Inc. as their health plan:
  Alamance, Caswell, Chatham, Durham, Franklin, Granville, Johnston, Nash, Orange, Person, Vance, Wake, Warren, and Wilson.
If a beneficiary reaches out with questions, please refer them to call the Medicaid Managed Care Call Center at 833-870-5500
Please look for upcoming Weekly Communication emails for more information
Web sites, comparison chart

## Slide 8: Expanded/Former Foster Care Children
Researching issue: reported some individuals not receiving full Medicaid, but only Family Planning
  DHB requesting report of all individuals with foster care evidence not receiving full Medicaid
Former Foster Care Children (MFC) – to age 26
  Children who aged out at 18 (or older) in NC
  Were in foster care and receiving Medicaid in NC
  Eligible for continued Medicaid without regard to income (evaluated for other MAGI programs first)
  Family Planning is program of last resort – if not eligible for any full Medicaid program (MIC, MIC-1, MAF-C/N, Expanded, MFC)
Expanded Foster Care – to age 21
  Children who aged out at 18 in any state
  Eligible without regard to income (evaluated for other MAGI programs first)
Caseworker should ensure current/former foster care evidence is in NC FAST

## Slide 9: FFM Open Enrollment
Annual open enrollment for the Federally Facilitated Marketplace (FFM):
begins November 1, 2019
ends December 15, 2019
Medicaid | OCTOBER 2019

## Slide 10: Questions