## Slide 1: NC Dual Eligibles Advisory Committee September 23, 2016
Department of Health and Human Services Division of Health Benefits

## Slide 2
Welcome
NC Department of Health and Human Services
Dee Jones
Dave Richard

## Slide 3
Member Introductions
Dual Eligibles Report Timeline
Status of Data Requests
Prior Advisory Committee Results
Group Discussion
Next Steps
Agenda

## Slide 4
Member Introductions

## Slide 5
Dual Eligibles Report Timeline
TASK | DURATION | START | FINISH | RESOURCE | Aug-15 | Aug-22 | Aug-29 | Sep-05 | Sep-12 | Sep-19 | Sep-26 | Oct-03 | Oct-10 | Oct-17 | Oct-24 | Oct-31 | Nov-07 | Nov-14 | Nov-21 | Nov-28 | Dec-05 | Dec-12 | Dec-19 | Dec-26 | Jan-02 | Jan-09 | Jan-16 | Jan-23 | Jan-30
Present Report Timeline |  | Aug-23 | Aug-23 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Propose Report Structure | 24 days | Aug-23 | Sep-23 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Review Provided Information | 24 days | Aug-23 | Oct-23 | Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DEAC Written Recommendations | 40 days | Oct-23 | Nov-17 | Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Work on Report | 65 days | Sep-26 | Dec-23 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Send Near Final Report to Team |  | Jan-03 | Jan-03 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1Team Review / Feedback | 4 days | Jan-03 | Jan-06 | All Parties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Revisions based on Team Feedback | 3 days | Jan-06 | Jan-10 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Send to DHHS Executive Team |  | Jan-11 | Jan-11 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DHHS Executive Team Review |  | Jan-11 | Jan-16 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Edits | 6 days | Jan-16 | Jan-23 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Submit Report |  | Jan-31 | Jan-31 | DHHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 Team Review consists of the Advisory & Steering Committees along with the DHHS Planning Team
Denotes Advisory Committee Meetings

## Slide 6
Status of Data Requests

## Slide 7
More up-to-date enrollment
Eligibility group descriptions
Population by region and rural/urban status
Population by living arrangement
Explanation for Medicaid-only disabled enrollment
List of mandatory vs. optional services
Population served by medical homes
MLTSS Utilization Changes (sent 9/2)
Completed Requests

## Slide 8
Status of Outstanding Requests
Request | Status
Diagnosis/Co-morbidity data | Requested internally; may only include FFS data
Additional detail on HMO premiums | Requested internally
Split out utilization and claims by partial vs. full duals | Requested internally
Distribution of claims to identify high utilizers | Requested internally
Income levels of people who qualify for spend down | Requested internally
Volume of services utilized | Requested internally
Number of duals utilizing services through LME-MCOs | Requested from consultant
Incorporation of Medicare data | Medicare data is not available; not feasible to obtain in the time period for the Dual Eligibles Advisory Committee

## Slide 9
Prior Advisory Committee Results
During the last meeting, the Duals Advisory Committee responded to four questions related to how and when the duals population should be incorporated into managed care.
The Steering Committee then reviewed these responses and worked to consolidate them into very specific recommendations.

## Slide 10
Summary Outcomes from Prior Discussions
Duals should be implemented after managed care has been proven with the Medicaid-only population.
Integration of duals into managed care should be conducted in carefully planned phases based on services and other key considerations.
Partial duals should not be included in the initial implementation of duals into managed care.

## Slide 11
Now that we know who should be integrated into managed care, and when this should occur, let’s talk more about how they should be integrated.
Digging Deeper…
Waiver Goals
Care coordination
Behavioral health
Readiness

## Slide 12
  Include the group’s perspective of recommendations shared in these materials.
  Whole Person Care Workgroup
  Consumer Experience in Medicaid Managed Long-Term Services and Supports Programs
Group Discussion

## Slide 13
Ensuring Quality, Integrated Services: The Dually Eligible Beneficiary Experience

## Slide 14
NC’s 1115 Waiver Application includes a number of LTSS-related goals that health plan design should address [Section 2.3.1.4].
  Support and build a system that promotes consumer choice
  Build upon current system by ensuring continued access to facility-based services when necessary, and expanding continuum of services and variety of settings in which to receive them
  Promote use of enabling technology
  Invest in service strategies that prevent, delay or avert need for Medicaid-funded LTSS through appropriate upstream interventions
  Recognize and bolster key role family caregivers and other natural supports play in supporting beneficiaries with long-term care needs to delay or divert use of institutional services
  Ensure that LTSS beneficiaries have access to, as needed, hands-on streamlined service coordination that is responsive to their clinical and social needs
  Focus on care transitions and opportunities for early interventions related to transition planning
What, if any, are the “Duals-specific” considerations as NC works to address each of these goals in health plan structure?
What additional goals that are not reflected in this list need to be considered for the LTSS needs of Duals and NC’s aging population to be effectively addressed in the health plan design?
LTSS Goals Identified in NC’s 1115 Waiver Application

## Slide 15
Research and experience, including recommendations which emerged from the DHHS Whole Person Work Group, recognize the essential role of care coordination in a quality, integrated managed program.
Are there any additional considerations about care coordination that need to be added to the Whole Person Care workgroup recommendations?
What are the special considerations for care coordination design as it relates to the Duals specifically?
  Management of chronic illness?
  Specific capacities/sensitivities around supporting older adults and people with physical disabilities?
  Specific capacities in coordinating Medicare-funded benefits/services?
Are there specific capacities that need to be developed to better facilitate outcomes related to social determinants of health?
  Adequate housing
  Viable employment opportunities
  Effective transportation.
What additional questions or “unknowns” did this conversation generate?
Care/Service Coordination

## Slide 16
NC’s 1115 Waiver Application indicates “[t]he clinical integration of behavioral health (encompassing mental health and substance use disorders) and primary care is a priority for North Carolina.” [See section2.3.1.3, NC 1115 Waiver Application, June, 2016]. Many Duals are dually eligible because of behavioral health-related disabilities and are currently served by NC DHHS’ LME-MCOs.
  Based on your experience, what are the considerations for ensuring individuals who are accessing services through both a PHP and an LME-MCO have the most integrated, coordinated experience possible?
  What additional questions or “unknowns” did this conversation generate?
Behavioral Health

## Slide 17
The importance of “readiness” prior to a state transitioning into a Medicaid managed delivery model is well documented.
  Readiness requires meaningful input and feedback from beneficiaries. Yet, many standard methods for engaging stakeholders in dialogue may be ineffective for engaging dually eligible beneficiaries, who may disproportionately experience challenges related to transportation and internet access. What are some methods NC can use to ensure beneficiary education, input and feedback throughout the Reform process?
  Duals’ enrollment into a Medicare managed care program is voluntary. This becomes a consideration if NC pursues a Medicaid/Medicare integrated service delivery model. What are the essential topics that individuals counseling beneficiaries on enrollment options (enrollment brokers) will need to discuss to assist the dually eligible beneficiary in making an informed decision about whether to enroll?
  What are the key milestones that need to be met for determining readiness for the transition to managed care for dually eligible beneficiaries? In other words, how will the State know the best time to go live with managed care?
Evidence of Readiness

## Slide 18
Advisory Committee: Develop the full written recommendations that will be incorporated into the Legislative Report
DHHS: Develop the Legislative Report
Next Steps