## Non-Development WG Goals
Goal Area 2; Non-Development Housing Activities
Goal Area 2, Objective 1
Secure housing resources and supports to increase access to affordable housing for the Plan’s focus population statewide within five years.
Strategies to Secure Housing Resources and Supports | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Establish baseline measures for this objective by gathering appropriate data from relevant agencies and partners within 2 years. | ST, Year 1 | NCDHHS, Interagency Council for Coordinating Homeless Programs (ICCHP), Advocates | High | August 2024 |  | In Progress
b. Increase the use of peer support across housing services (e.g., housing search/navigation, case management, connection to services). | ST, Year 1 | NCDHHS, managed care organizations (MCOs), service providers | High |  |  | Not Started
c. Work with developers and other partners to identify existing Low Income Housing Tax Credit (LIHTC) properties nearing their end of affordability and identify resources and strategies in order to offer incentives to current project owners with the goal that the properties remain affordable. | ST, Year 1 | NCHFA | High |  |  | Not Started
Goal Area 2, Objective 2
Secure resources for long-term rental assistance; better utilize, prioritize, and target existing rent assistance and subsidized housing for the target population statewide within five years.
Strategies to Strengthen Rental Assistance for NCDHHS Priority Populations | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Establish baseline measures for this objective by gathering appropriate data from relevant agencies and stakeholders within 2 years. | ST, Year 1 | NCDHHS, ICCHP, Advocates | High | August 2024 |  | In Progress
Goal Area 2, Objective 3
Promote the use of reasonable use of eviction, criminal and credit records when screening potential tenants to provide protections for those searching for housing.
Strategies to Improve Access and Stability in Housing for NCDHHS Priority Populations | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Working with NCHFA, evaluate options to lower screening barriers (exclude prior eviction from screening) and reform the referral process for all NCHFA/NCDHHS funded properties including a review of requirements for income & making all services optional for qualified applicants (Housing First). | ST, Year 1 | NCDHHS, with support from NCHFA, NC Justice Center, NC Fair Housing Project | High |  |  | Not Started
Goal Area 2, Objective 4
Increase the quality of existing affordable private market units by year 5 of the Plan.
Strategies to Improve the Quality of Affordable Private Market Units | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
No Year 1 goals identified
Goal Area 2, Objective 5
Increase eviction prevention and diversion support to tenants across the state, resulting in an overall reduction of evictions from year 1 to year 5 of this plan.
Strategies to Increase Eviction Prevention and Diversion Support | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Establish baseline measures for this objective by gathering appropriate data from relevant agencies and stakeholders within 2 years. | ST, Year 1 | NCDHHS with support from NCHFA | High |  |  | Not Started

## (HSPA) Services WG Goals
Goal Area 3: Services
Goal Area 3, Objective 1
In the first year of the Plan, identify all funding streams that can be used to support pre-tenancy, transition, and tenancy support services (including the various Medicaid service definitions) along with their target populations, caps/limitations, amounts, and departments that currently fund services for all populations.
Strategies to Fund Housing Services | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Establish definitions of pre-tenancy and tenancy sustaining services that apply to all populations covered by the Strategic Housing Plan (within one year to 18 months of plan launch). | ST, Year 1 | NCDHHS | High | August 2024 |  | In Progress
b. Identify available funding sources for services, including those resources not administered by DHHS, by target population (within one year to 18 months of plan launch). | ST, Year 1 | NCDHHS | High | February 2024 |  | In Progress
Goal Area 3, Objective 2
By 6/30/2027, create regional tenancy support service providers to provide housing navigation and support services to people within their geographic region, regardless of disability type or target population, in order to increase access, quality, and oversight of services in the state.
Strategies to Create Regional Tenancy Support Service Providers | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Identify providers of quality services by population and county/region | ST, Year 1 | NCDHHS, managed care organizations (MCOs), NC Coalition to End Homelessness (NCCEH) supporting in Balance of State CoC regions | High |  |  | Not Started
Goal Area 3, Objective 3
By 12/31/2027, develop a training program on the delivery of evidence-based and best practices, including trauma-informed care, for identified providers of pre-tenancy, transition, and tenancy support, and/or for residential service providers.
Strategies to Develop an Evidence-Based and Best Practices Training Program for Service Providers | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Identify and compile existing sources of trainings on pre-tenancy and tenancy-sustaining services, including in the homeless response system. | ST, Year 1 | NCDHHS, Managed Care Orgs (MCOs), Continuums of Care (CoCs) | High | August 2024 |  | In Progress

## Coord. and Partnership WG Goal
Goal Area 4: Coordination
Goal Area 4, Objective 1
Create a formal structure for accountability and shared strategy for all housing functions across state agencies and key partners in year one of this Plan.
Strategies to Create a Formal Structure | Short Term/Long Term | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Stand up the North Carolina Interagency Council on Coordinating Homeless Programs (ICCHP) by June 2022 (in progress currently). | ST, Year 1 | NC. Gov. (NCDHHS to advocate, advise, and support) | High - Completed | 2022-08-01 | June 2022 | Completed
b. Establish ICCHP State Agency Workgroup to better coordinate programs and funding across state government. | ST, Year 1 | NC. Gov. and ICCHP (NCDHHS to advocate, advise, and support) | High | August 2024 |  | In Progress
c. ICCHP to support and promote effective interagency collaboration and system integration, including coordination of state and federal funding, and setting shared priorities for investments. | ST, Year 1 | NC. Gov. and ICCHP (NCDHHS to advocate, advise, and support) | High | August 2024 |  | Ongoing
d. Create transparency, accountability, and opportunities for cross-departmental partnerships for all federal and state funding resources focused on affordable rental housing and including COVID-related, new, and existing funding resources. | ST, Year 1 | NC Gov. (NCDHHS to advocate, advise, and support) | High | August 2024 |  | Ongoing
Goal Area 4, Objective 2
Explore the possibility of coordinating or consolidating housing functions across NCDHHS.
Strategy to Coordinate Housing Activities | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Explore the opportunity for a Housing and Homelessness Unit in NCDHHS to begin coordinating all housing functions across divisions and/or oversee NCDHHS housing programs; collaborate across NCDHHS divisions to create department-wide housing goals and coordinate housing activities across the department. | ST, Year 1 | NCDHHS | High | August 2024 |  | In Progress
Goal Area 5: Partnerships
Goal Area 5, Objective 1
With the goal of aligning messaging, increasing coordination among housing partners, and lowering barriers while increasing access for the focus population of this Plan, increase communication between housing agencies including NCDHHS, NCHFA, NCORR, NC Commerce, NC Department of Administration, NC Department of Public Safety (Corrections), PHAs, CoCs, local housing & service providers, and HUD.
Strategy to Increase Communication | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Establish a communication network with housing providers (e.g., gathering contact information for organizations and government entities providing housing, homelessness, and pre-tenancy and tenancy supportive services) across the state to successfully disseminate information on evidence-based and best practices as well as NCDHHS’ housing programs, guidance, and goals | ST, Year 1 | NCDHHS | High | August 2024 |  | In Progress
d. Adopt a uniform definition of permanent supportive housing (PSH) (based on evidence-based practice definition) to facilitate a cross-disability PSH approach within state government and local communities. See Goal Area 1, Objective 1.c. | ST, Year 1 | NCDHHS | High | August 2024 |  | See Note
Goal Area 5, Objective 2
Review existing public-private partnerships for housing development across the state and replicate or create new partnerships in at least three additional areas, cities, or towns focused on housing development by the end of year 5.
Strategy to Increase Partnerships | Time Frame (Short Term or ST/Long Term or LT) | Resp. Parties | High or Low Priority | Start Date | Completion Date | Status
a. Explore housing data to determine the needs for affordable units by affordability level. If data are currently not sufficient, consider engaging a consulting firm to conduct a market study across the state. | ST, Year 1 | NCDHHS with support from NC Housing Finance Agency (NCHFA), Interagency Council on Coordinating Homeless Programs (ICCHP), and localities (e.g., Consolidated Plan and other needs assessment data) | High | August 2024 |  | In Progress